## Sheet1
WBS | TASK | START DATE | DUE DATE | DURATION | JUNE | [14 empty] | JULY
[5 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
1 | SPRINT 1 | bar: JUNE 16 to JUNE 21; JUNE 23 to JUNE 28; JUNE 30 to JULY 3
1.2 | Frontend: Setup framework and build pipeline | 16/06/2025 | 16/06/2025 | 1 | bar: JUNE 16
1.3 | Frontend: Google platform API integration | 16/06/2025 | 16/06/2025 | 1 | bar: JUNE 16
1.4 | Frontend: Maps view and user interaction | 16/06/2025 | 16/06/2025 | 1 | bar: JUNE 16
1.5 | Frontend: Ploting places and geocoding | 17/06/2025 | 18/06/2025 | 2 | bar: JUNE 17 to JUNE 18
1.6 | Frontend: Point to point routing | 18/06/2025 | 20/06/2025 | 3 | bar: JUNE 18 to JUNE 20
2 | SPRINT 2 | bar: JUNE 16 to JUNE 21; JUNE 23 to JUNE 28; JUNE 30 to JULY 3
2.1 | Backend: API and database design | 21/06/2025 | 21/06/2025 | 1 | bar: JUNE 21
2.2 | Backend: Project skeleton | 21/06/2025 | 21/06/2025 | 1 | bar: JUNE 21
2.3 | Backend: Maps and custom route/places endpoint | 23/06/2025 | 23/06/2025 | 1 | bar: JUNE 23
2.4 | Backend: User and auth endpoint | 24/06/2025 | 24/06/2025 | 1 | bar: JUNE 24
2.5 | Backend: Websocket and report endpoint | 25/06/2025 | 26/06/2025 | 2 | bar: JUNE 25 to JUNE 26
3 | SPRINT 3 | bar: JUNE 16 to JUNE 21; JUNE 23 to JUNE 28; JUNE 30 to JULY 3
3.1 | Web: Backend and frontend integration | 25/06/2025 | 26/06/2025 | 2 | bar: JUNE 25 to JUNE 26
3.2 | Frontend: Essential UI elements | 27/06/2025 | 28/06/2025 | 2 | bar: JUNE 27 to JUNE 28
3.3 | Web: Finalize project | 30/06/2025 | 30/06/2025 | 1 | bar: JUNE 30
3.4 | Mobile: Capacitor build setup and android emulator | 01/07/2025 | 01/07/2025 | 1 | bar: JULY 1
3.5 | Testing and review | 02/07/2025 | 03/07/2025 | 2 | bar: JULY 2 to JULY 3